EDS MIGRATION — COMPARATIVE ANALYSIS

Bed Bath N' Table — Australia vs Singapore

Commonalities and variations across the two storefronts

This document compares the migration scope of the two Bed Bath N’ Table storefronts analysed — the Australian flagship (bedbathntable.com.au) and the Singapore site (bedbathntable.com.sg) — to highlight what can be reused across both and where they diverge.

1. At-a-Glance Comparison

| Dimension | Australia (AU) | Singapore (SG) | Verdict |
| --- | --- | --- | --- |
| Platform | Adobe Commerce (Magento 2) + PageBuilder | Adobe Commerce (Magento 2) + PageBuilder | Common |
| CDN | Fastly | Fastly | Common |
| Sitemap URLs | 2,860 | 6,756 | Variation (SG larger) |
| Product pages (PDP) | 2,033 | ~5,165 | Variation |
| Functional templates | 7 | 8 (functional) | Mostly common |
| Block variants catalogued | 102 | 61 | Variation (AU richer) |
| Sample analysed | 77 pages (0 failed) | 51 pages (27 failed / stale) | Variation |
| Sitemap quality | Clean, categorized (products/categories/cms/pages) | Single sitemap, ~35% stale/404 | Variation |
| Store locator | Dedicated template (~170 pages) | Not present as template | Variation (AU only) |
| Experimentation | AB Tasty (A/B + personalization) | Not detected | Variation (AU only) |
| Payment methods | Afterpay, PayPal, Zip, Apple Pay, Google Pay | Afterpay, PayPal | Variation (AU richer) |
| EDS RUM pilot (rum.hlx.page) | Present | Present | Common |

2. Commonalities (Reusable Across Both)

The two sites share the same brand, platform and design system, so a large share of migration work is reusable.

Shared platform & architecture

- Identical stack: Adobe Commerce (Magento 2) with PageBuilder content, fronted by Fastly CDN.

- Same commerce model: catalog-driven PDPs, faceted PLPs, category landings, cart/checkout/wishlist.

- Both already load Adobe Edge Delivery RUM (rum.hlx.page) — an EDS measurement pilot is in place on each.

Shared templates

| Template | AU | SG |
| --- | --- | --- |
| commerce-standard (home/category/PLP/PDP shell) | Yes (63) | Yes (43) |
| product-detail (PDP) | Yes | Yes |
| product-listing (PLP) | Yes | Yes |
| category-landing | Yes | Yes |
| blog / editorial content | Yes (4) | Yes (2 article + editorial) |
| CMS / static | Yes | Yes (in content-editorial) |

Shared blocks (same base components)

Base blocks present on BOTH sites — these can be built once and reused, with per-site design variations:

| Base block | AU variants | SG variants |
| --- | --- | --- |
| header (global) | 1 | 1 |
| footer (global) | 1 | 1 |
| hero | 12 | 13 |
| form (search/newsletter/cart/filters) | 22 | 20 |
| carousel | 19 | 4 |
| columns | 15 | 5 |
| cards | 2 | 1 |
| tabs | 1 | 5 |
| video | 2 | 2 |
| embed | 2 | 2 |
| custom / unknown (PageBuilder comps) | 20 | 7 |

3. Variations (Site-Specific)

AU-only features

- Store-locator template: ~170 uniform store pages (address, hours, Get Directions, map, "Search Other Stores"). Requires Google Maps integration and a store data feed.

- AB Tasty experimentation layer (A/B testing + personalization) site-wide — adds a migration decision: migrate experiments or rebuild.

- Richer payments: Zip, Apple Pay and Google Pay in addition to Afterpay + PayPal.

- Google Maps API (store locator) and a dedicated table block (4 variants) for store hours / size guides.

- Higher block diversity: 102 variants vs 61 — notably more carousel (19 vs 4) and columns (15 vs 5) variants, reflecting a more heavily merchandised flagship.

SG-only / SG-heavier characteristics

- Larger raw catalog: 6,756 sitemap URLs (~5,165 PDPs) vs 2,860 — but with ~35% stale/404 entries needing a validation crawl.

- More tabs variants (5 vs 1) — PDP info tabs/accordions used more.

- Single un-categorized sitemap (vs AU’s clean products/categories/cms/pages split).

Template-count nuance

AU discovery separated store-locator, size-guide and CMS/guide as distinct templates (7 total); SG collapsed content into a broader "content-editorial" group (4 total). Functionally both sites cover the same page types — the difference is granularity, not fundamentally different page kinds.

4. Migration Implications

| Aspect | Implication |
| --- | --- |
| Shared build | Build the commerce block library and templates ONCE; both sites reuse ~70–80% of blocks with design-variation theming. |
| Sequencing | Do AU first (cleaner sitemap, store-locator + AB Tasty force the harder integrations early), then SG largely reuses the library. |
| SG data hygiene | SG needs a URL-validation crawl to strip ~35% stale entries before final counts/import. |
| AU integrations | AU adds Google Maps (store locator), AB Tasty, and 3 extra payment methods — scope these as AU-specific. |
| PDP automation | Both: PDPs are data-driven and bulk-automatable from the Magento catalog — the largest volume is the least effort. |
| Reuse estimate | A combined program is materially cheaper than two standalone migrations due to shared blocks/templates. |

5. Effort & Cost Comparison

| Metric | Australia (AU) | Singapore (SG) |
| --- | --- | --- |
| Total effort (standalone) | ~99–146 person-days | ~90–130 person-days |
| Calendar schedule | ~13–19 weeks | ~12–18 weeks |
| Indicative cost (~$600/day) | ≈ $59k–$88k | ≈ $54k–$78k |
| Auto-migratable pages | ~77% | ~77% |
| Key cost drivers | Store locator, AB Tasty, 5 payments, 102 blocks | Large catalog, stale-URL cleanup, PLP facets |

Combined-program note: because ~70–80% of blocks and all core commerce templates are shared, running both migrations as one program (shared library, per-site theming and content) is expected to cost significantly less than the sum of the two standalone estimates above.

6. Recommendation

- Treat AU and SG as a single multi-site program on a shared EDS block library and template set.

- Build and harden on AU first (it forces store-locator + AB Tasty + full payments), then apply to SG with theming + content.

- Run a URL-validation crawl on SG before import to remove stale sitemap entries.

- Automate PDPs on both via the Magento catalog feed; reserve manual effort for merchandised home/campaign pages.

- Decide early whether AB Tasty experiments migrate or are rebuilt in the EDS experimentation model.

Bed Bath N' Table — AU vs SG Comparative Analysis · Generated 2026-08-27 · Green = commonality, amber = variation. Content/presentation-layer scope; Adobe Commerce backend assumed retained.